## bottleneck_database
bottleneck_id | name | category | subcategory | jurisdiction | agency | legal_authority | timeline_statutory_days | timeline_typical_months | timeline_range_months | timeline_with_litigation_months | description | key_delay_factors | quantitative_impact | affected_project_types | recent_changes | reform_status | source_url
FERC_PIPELINE_CERT | FERC Pipeline Certificate Review | FEDERAL_PERMITTING | Pipeline Infrastructure | FEDERAL | FERC | Natural Gas Act Section 7 |  | 18 | 12-48 | 60 | Certificate of Public Convenience and Necessity for interstate natural gas pipelines. | NEPA EIS preparation; CWA Section 401 state certification; ESA Section 7 consultation; landowner opposition; GHG emissions analysis | No statutory time limit; ~95% approval rate historically; 20% of projects delayed 90+ days beyond FERC deadline | Interstate natural gas pipelines | DC Circuit vacated Transco REAE pipeline (July 2024) for inadequate GHG analysis; increased uncertainty | Certificate Policy Statement under review since 2022 | https://www.ferc.gov/industries-data/natural-gas/overview/certificate-applications
LNG_FERC_APPROVAL | LNG Terminal FERC Authorization | FEDERAL_PERMITTING | LNG Infrastructure | FEDERAL | FERC | Natural Gas Act Section 3 |  | 36 | 24-60 | 84 | FERC authorization for siting, construction, and operation of onshore LNG export terminals. | Full EIS required; environmental justice review; GHG emissions analysis; state and local permits; community opposition | Average 158 days from EIS to approval (2015-2022); 20 FERC approvals totaling 27.2 Bcf/d capacity | LNG export terminals, LNG import terminals | Trump administration 2025 expedited procedures; FERC considering blanket authorization for routine modifications | November 2025 NOI on streamlining LNG approvals | https://www.ferc.gov/natural-gas/lng
DOE_LNG_EXPORT | DOE LNG Export Authorization | FEDERAL_PERMITTING | LNG Exports | FEDERAL | DOE | Natural Gas Act Section 3 |  | 12 | 3-36 | 48 | DOE authorization for LNG exports. FTA countries automatic. Non-FTA requires public interest determination. | Biden LNG pause (Jan 2024); economic/environmental review methodology under revision; litigation | ~50 Bcf/d approved capacity; 14.28 Bcf/d operating; ~10 Bcf/d affected by pause | LNG export terminals | Biden LNG pause on non-FTA authorizations (Jan 2024); 7-year export commencement deadline policy (2023) | Pause in effect; Trump administration expected to lift pause | https://www.energy.gov/fecm/regulation-natural-gas-imports-and-exports
PJM_INTERCONNECTION | PJM Generator Interconnection Queue | GRID_INTERCONNECTION | RTO/ISO Queue | REGIONAL | PJM | FERC Order 2023 |  | 72 | 48-96 |  | PJM interconnection study process for new generation. Currently taking 6-8 years for projects entering 2018-2020. | Queue backlog from 2018-2020 projects; network upgrade costs ($240/kW average); restudy triggers; speculative projects | ~140 GW processed 2023-2024; 46 GW with signed agreements; 63 GW remaining; capacity prices jumped 10x due to queue delays | Solar, wind, battery storage, natural gas generation | PJM Transition Cycle 1 completed Sept 2024; 1-2 year study turnaround expected for new projects post-2026 | FERC Order 2023 implemented; first-ready, first-served model | https://www.pjm.com/
MISO_INTERCONNECTION | MISO Generator Interconnection Queue | GRID_INTERCONNECTION | RTO/ISO Queue | REGIONAL | MISO | FERC Order 2023 |  | 60 | 36-72 |  | MISO Definitive Planning Phase interconnection study process. Projects from 2018-2019 still in queue. | 242 GW in queue; 2023 queue window closed; 650-day average delays; 25 GW approved resources experiencing delays | 283 projects from 2022 cycle in Central region still awaiting study; 369 projects in South region | Solar, wind, battery storage | 2024 queue window delayed; 2023 projects expected to reach GIA execution by 2026 | Queue reforms implemented; backlog clearing expected by 2026 | https://www.misoenergy.org/
CAISO_INTERCONNECTION | CAISO Generator Interconnection Queue | GRID_INTERCONNECTION | RTO/ISO Queue | REGIONAL | CAISO | FERC Order 2023 |  | 48 | 24-60 |  | CAISO cluster study process for generator interconnection. | High queue volume; limited transmission capacity; restudy requirements | Only ~19% of projects nationally complete interconnection process (2000-2018) | Solar, wind, battery storage | Not accepting new applications in 2024 to clear backlog | FERC Order 2023 implementation underway | https://www.caiso.com/
CWA_401_CERT | Clean Water Act Section 401 Certification | FEDERAL_PERMITTING | Water Quality | STATE | STATE_DEQ | Clean Water Act Section 401 | 365 | 12 | 6-36 | 60 | State certification that federally permitted activities will comply with water quality standards. States can deny certification to block projects. | Scope of review (activity as a whole vs point discharge); state opposition to fossil fuel projects; pre-filing requirements | NY denied Constitution Pipeline (2016), Millennium Valley Lateral; WA denied coal export terminal (2017); OR denied Jordan Cove LNG | Pipelines, LNG terminals, power plants, hydropower, dredge/fill activities | Trump 2020 rule limiting scope reinstated by SCOTUS (Apr 2022); Biden 2023 rule expanded scope; Trump 2026 proposed rule to limit scope again | EPA proposed rule January 2026 to narrow scope and streamline timelines | https://www.epa.gov/cwa-401
CWA_404_PERMIT | Clean Water Act Section 404 Wetlands Permit | FEDERAL_PERMITTING | Wetlands | FEDERAL | ARMY_CORPS | Clean Water Act Section 404 |  | 9 | 1.5-18 | 36 | Army Corps permit for discharge of dredged or fill material into waters of the US including wetlands. | Alternatives analysis (LEDPA); mitigation requirements; Section 401 certification needed; NEPA compliance; ESA consultation | Individual permits: 264 days average (FY2018); Nationwide Permits: 45 days average; Emergency permits: expedited | Pipelines, transmission lines, infrastructure, mining, development | Sackett v EPA (2023) narrowed WOTUS jurisdiction; Trump emergency procedures using national energy emergency declaration | Nationwide Permit 12 for oil/gas pipelines requires individual 404 permits | https://www.epa.gov/cwa-404
NEPA_EIS | NEPA Environmental Impact Statement | FEDERAL_PERMITTING | Environmental Review | FEDERAL | MULTIPLE | National Environmental Policy Act | 730 | 36 | 24-84 | 120 | Full environmental review required for major federal actions significantly affecting environment. | Multi-agency coordination; public comment periods; alternatives analysis; litigation; staff capacity | Average EIS takes 4.5 years; 25% take 6+ years; energy projects average 4.5 years; transmission 6.5 years | Major pipelines, LNG terminals, transmission lines, power plants on federal land | Fiscal Responsibility Act 2023 imposed 2-year deadline; CEQ 2024 reforms; Trump emergency procedures (14 days for EA) | Ongoing reform efforts; categorical exclusions expanded for certain clean energy projects | https://ceq.doe.gov/
ESA_SECTION_7 | Endangered Species Act Section 7 Consultation | FEDERAL_PERMITTING | Species Protection | FEDERAL | FWS_NMFS | Endangered Species Act Section 7 | 135 | 6 | 3-18 | 36 | Consultation with FWS/NMFS to ensure federal actions do not jeopardize listed species or critical habitat. | Biological assessment preparation; formal consultation 90-day clock; extensions; BiOp litigation; multiple species | 35,000+ project review requests since Nov 2022; workload rising with IRA/IIJA projects | All federally permitted energy projects in areas with listed species | Trump emergency procedures allow expedited informal consultation under national energy emergency | 2024 rule changes; IPaC tool reduces staff time for 10% of projects | https://www.fws.gov/service/section-7-consultations
NHPA_106 | National Historic Preservation Act Section 106 | FEDERAL_PERMITTING | Cultural Resources | FEDERAL | ACHP | National Historic Preservation Act Section 106 |  | 12 | 3-24 | 36 | Review of federal undertakings for effects on historic properties. Consultation with SHPO/THPO and tribes required. | SHPO/THPO consultation timelines; tribal consultation; MOA negotiations; no statutory deadline | Can add 6-12 months to project timeline; particularly impacts linear infrastructure crossing multiple states | Pipelines, transmission lines, energy projects on federal land, federally funded projects | Trump emergency procedures: 7-day comment period under national energy emergency | NEPA substitution process under consideration for major EIS projects | https://www.achp.gov/protecting-historic-properties
TRANSMISSION_SITING | Interstate Transmission Line Siting | STATE_PERMITTING | Transmission Infrastructure | STATE | STATE_PUC | State Public Utility Laws |  | 60 | 36-120 | 144 | State-by-state approval for transmission line siting. No federal preemption except limited FERC backstop authority. | Multiple state approvals needed; local zoning; landowner opposition; lack of coordination; different standards per state | Average 4-11 years for permits; construction adds 2-4 years; some projects 10-12 years total | Interstate and interregional high-voltage transmission lines | IIJA 2021 clarified FERC backstop authority; DOE CITAP program aims for 2-year federal timeline | FERC backstop authority not yet used; 3 potential NIETCs identified Dec 2024 | https://www.energy.gov/gdo/transmission-siting-and-permitting-efforts
LOCAL_SOLAR_ZONING | Local Solar Zoning and Permitting | LOCAL_PERMITTING | Renewable Siting | LOCAL | COUNTY_TOWNSHIP | Local Zoning Ordinances |  | 12 | 3-48 | 60 | Local zoning approval for solar farms. Highly variable by jurisdiction. Many local bans or restrictions. | Local ordinance restrictions; community opposition; setback requirements; agricultural land restrictions; visual impact concerns | 760 projects rejected since 2013; 117 rejected in 2024 alone (78 solar, 39 wind); 73% increase in local restrictions 2022-2023; ~1/3 of projects cancelled; $2M average sunk cost per cancelled solar project | Utility-scale solar, community solar | Michigan shifted siting to PSC for projects >50 MW (Nov 2024); Ohio affirmed local rejection rights (2021) | Some states preempting local authority; others affirming local control | https://www.nrel.gov/
LOCAL_WIND_ZONING | Local Wind Turbine Zoning and Permitting | LOCAL_PERMITTING | Renewable Siting | LOCAL | COUNTY_TOWNSHIP | Local Zoning Ordinances |  | 18 | 6-60 | 72 | Local zoning approval for wind farms. Significant setback and noise restrictions in many jurisdictions. | Setback requirements (some 6,600 ft+); noise concerns; visual impact; community opposition; wildlife concerns | Average 14-month delay from community opposition; $7.5M average sunk cost per cancelled wind project; 39 wind projects rejected in 2024 | Utility-scale wind farms | Michigan shifted siting to PSC for projects >100 MW (Nov 2024); various states adding restrictions | Mixed trends: some states centralizing, others adding local restrictions | https://www.nrel.gov/
CAA_TITLE_V | Clean Air Act Title V Operating Permit | STATE_PERMITTING | Air Quality | STATE | STATE_DEQ | Clean Air Act Title V | 540 | 18 | 12-24 | 36 | Operating permit for major sources of air pollution. | Complex emission calculations; EPA oversight; public notice requirements; permit conditions negotiations | Required for power plants, refineries, large industrial facilities | Gas-fired power plants, coal plants, refineries, large industrial facilities | GHG permitting requirements; Good Neighbor NOx limits affecting some states | Standard permitting timelines; varies by state | https://www.epa.gov/title-v-operating-permits
CAA_PSD | Clean Air Act PSD/NSR Preconstruction Permit | STATE_PERMITTING | Air Quality | STATE | STATE_DEQ | Clean Air Act PSD/NSR | 365 | 12 | 6-24 | 48 | Preconstruction permit for new or modified major sources in attainment areas (PSD) or nonattainment areas (NSR). | BACT/LAER determination; air quality modeling; public comment; EPA Region review | Required before construction of major sources; can affect project timeline by 6-18 months | New power plants, major plant modifications, large industrial facilities | GHG BACT requirements; EPA 111 rule implications | Standard process; varies by state | https://www.epa.gov/nsr
CZMA_CONSISTENCY | Coastal Zone Management Act Consistency | STATE_PERMITTING | Coastal Resources | STATE | STATE_COASTAL | Coastal Zone Management Act | 180 | 6 | 3-12 | 24 | State certification that federally licensed activities are consistent with state coastal management programs. | State coastal program requirements vary; can be used to delay/block projects; similar to Section 401 | Required for LNG terminals, offshore wind, coastal pipelines | LNG terminals, offshore wind, coastal infrastructure, pipelines crossing coastal zones | Active in offshore wind permitting | Standard process | https://coast.noaa.gov/czm/

## by_category
category | count
FEDERAL_PERMITTING | 8
GRID_INTERCONNECTION | 3
LOCAL_PERMITTING | 2
STATE_PERMITTING | 4

## timelines
bottleneck_id | name | category | jurisdiction | agency | timeline_typical_months | timeline_range_months | timeline_with_litigation_months
PJM_INTERCONNECTION | PJM Generator Interconnection Queue | GRID_INTERCONNECTION | REGIONAL | PJM | 72 | 48-96
TRANSMISSION_SITING | Interstate Transmission Line Siting | STATE_PERMITTING | STATE | STATE_PUC | 60 | 36-120 | 144
MISO_INTERCONNECTION | MISO Generator Interconnection Queue | GRID_INTERCONNECTION | REGIONAL | MISO | 60 | 36-72
CAISO_INTERCONNECTION | CAISO Generator Interconnection Queue | GRID_INTERCONNECTION | REGIONAL | CAISO | 48 | 24-60
NEPA_EIS | NEPA Environmental Impact Statement | FEDERAL_PERMITTING | FEDERAL | MULTIPLE | 36 | 24-84 | 120
LNG_FERC_APPROVAL | LNG Terminal FERC Authorization | FEDERAL_PERMITTING | FEDERAL | FERC | 36 | 24-60 | 84
FERC_PIPELINE_CERT | FERC Pipeline Certificate Review | FEDERAL_PERMITTING | FEDERAL | FERC | 18 | 12-48 | 60
LOCAL_WIND_ZONING | Local Wind Turbine Zoning and Permitting | LOCAL_PERMITTING | LOCAL | COUNTY_TOWNSHIP | 18 | 6-60 | 72
CAA_TITLE_V | Clean Air Act Title V Operating Permit | STATE_PERMITTING | STATE | STATE_DEQ | 18 | 12-24 | 36
CAA_PSD | Clean Air Act PSD/NSR Preconstruction Permit | STATE_PERMITTING | STATE | STATE_DEQ | 12 | 6-24 | 48
CWA_401_CERT | Clean Water Act Section 401 Certification | FEDERAL_PERMITTING | STATE | STATE_DEQ | 12 | 6-36 | 60
DOE_LNG_EXPORT | DOE LNG Export Authorization | FEDERAL_PERMITTING | FEDERAL | DOE | 12 | 3-36 | 48
NHPA_106 | National Historic Preservation Act Section 106 | FEDERAL_PERMITTING | FEDERAL | ACHP | 12 | 3-24 | 36
LOCAL_SOLAR_ZONING | Local Solar Zoning and Permitting | LOCAL_PERMITTING | LOCAL | COUNTY_TOWNSHIP | 12 | 3-48 | 60
CWA_404_PERMIT | Clean Water Act Section 404 Wetlands Permit | FEDERAL_PERMITTING | FEDERAL | ARMY_CORPS | 9 | 1.5-18 | 36
ESA_SECTION_7 | Endangered Species Act Section 7 Consultation | FEDERAL_PERMITTING | FEDERAL | FWS_NMFS | 6 | 3-18 | 36
CZMA_CONSISTENCY | Coastal Zone Management Act Consistency | STATE_PERMITTING | STATE | STATE_COASTAL | 6 | 3-12 | 24